GOVERNMENT OF PAKISTAN

Planning Commission

Ministry of Planning, Development & Reform

(Public Investment Authorization Section)

### *******

Extension in execution period of development projects from DDWP / CDWP / ECNEC

- Name of sponsoring Ministry / Agency:	Kashmir Affairs & Gilgit Baltistan Division

- Name of Executing Agency: 			Public Works Department Govt. of AJ&K

- Sector / sub sector: 				T&C

(Rs. in million)

| 1 | Name of the Project: |  |  |  |  | Improvement & Reconditioning of Noseri Leswa by-pass road length 52-km District Muzaffarabad/Neelum |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Location : |  |  |  |  | District Muzaffarabad and District Neelum |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Date of Approval: |  |  |  |  | DDWP |  |  |  |  | CDWP |  |  |  |  |  | ECNEC |  |  |  |
| (a) | Original: |  |  |  |  |  |  |  |  |  | 26/12/2013 |  |  |  |  |  |  |  |  |  |
| (b) | Last revised, if any: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Approved cost : |  |  |  |  | Total |  |  |  |  | Local |  |  |  |  |  | FEC |  |  |  |
| (a) | Original: |  |  |  |  | 878.650 Million |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (b) | Last revised, if any: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Objectives (in bullet form) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Commencement date |  |  |  |  | As per original PC-I |  |  |  |  |  |  | Actual |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 25/06/2014 |  |  |  |  |  |  | 27/12/2016 |  |  |  |  |  |  |  |
| 7 | Completion Date |  |  |  |  | As per original / revised PC-I |  |  |  |  |  |  | Expected |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 30th June 2017 |  |  |  |  |  |  | 31st December 2019 |  |  |  |  |  |  |  |
| 8 | Year-wise financial phasing, releases and utilization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Fiscal Year |  | Phasing as per approved PC-I (latest) |  | PSDP allocation |  |  |  | Actual amount released |  |  |  |  |  |  | Actual utilization |  |  |  |  |
|  |  |  | Total | FEC | Total |  | FEC |  | Total |  |  | FEC |  |  | Total |  |  |  | FEC |  |
|  | 1 |  | 2 | 3 | 4 |  | 5 |  | 6 |  |  | 7 |  |  | 8 |  |  |  | 9 |  |
|  | 2014-15 |  | 283.391 | - | 100.000 |  | - |  | 100.000 |  |  | - |  |  | 1.000 |  |  |  | - |  |
|  | 2015-16 |  | 322.773 | - | 100.000 |  | - |  | 100.000 |  |  | - |  |  | - |  |  |  | - |  |
|  | 2016-17 |  | 272.486 | - | 120.000 |  | - |  | 120.000 |  |  | - |  |  | 120.000 |  |  |  | - |  |
|  | 2017-18 |  | - | - | 558.650 |  | - |  | 50.000 |  |  | - |  |  | 35.323 |  |  |  | - |  |
| 9 | Itemized cost as per approved PC-I and utilization (major items) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | S # | Major items |  |  |  |  |  | PC-I Provision |  |  |  |  |  | Cumulative utilization upto date |  |  |  | Balance |  |  |
|  |  |  |  |  |  |  |  | Quantity |  | Cost estimates |  |  |  |  |  |  |  | Work to be done (Qty) |  | Funds required |
|  | 1 | 2 |  |  |  |  |  | 3 |  | 4 |  |  |  | 5 |  |  |  | 6 |  | 7 |
|  | i | Earth Work i/c filling |  |  |  |  |  | 10915280 (Cft) |  | 68.112 |  |  |  | 7.260 |  |  |  | 10384999cft |  |  |
|  | ii | Retaining Structure i/c all activities |  |  |  |  |  | 1374525 (Cft) |  | 131.365 |  |  |  | 34.482 |  |  |  | 1007792cft |  |  |
|  | iii | Cross Drainage |  |  |  |  |  | 110 (No.) |  | 71.934 |  |  |  | 1.576 |  |  |  | 65 Nos |  |  |
|  | iv | Mett: & B Topping (Premix) |  |  |  |  |  | 52-Km |  | 499.132 |  |  |  | 31.212 |  |  |  | 42Km |  |  |
| s | v | Parapets |  |  |  |  |  | 10500 (Nos) |  | 26.565 |  |  |  | - |  |  |  | 10400 Nos. |  |  |
|  | vi | Escalation/Contingencies/slop Protection |  |  |  |  |  |  |  | 81.542 |  |  |  | - |  |  |  | 81.542 |  |  |
| 10. | - Physical progress ( % ): Earth Work 5% Sub base & base course 53% Asphalt 18% Cross Drainage 41% Retaining Structure 27% Parapets 1% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 | No. of previous extensions ( indicate approving authority and period with dates): Nil |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 | Extension required ( indicate period with dates): 31st December 2019 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13. | Main reasons / justification for extension: PC-1 of mentioned project was approved CDWP through Ministry of Kashmir Affairs and Gilgit Biltistan on 26th December 2013 at cost of Rs. 878.650 Million and Admin approval was issued on 25th June 2014. The Federal Govt. approved the award of said project to FWO on single source basis vide No. PC/18/2013 dated 24th August 2015. FWO received the bidding documents on 22-09-2015. FWO submitted their rates on 03/12/2015 which were much higher than the approved PC-I rates. Series of meetings at different places and forums were held about the rationalization of rates for said project with FWO. FWO was submitted their rationalized rates on 25th May 2016 and then Letter of Acceptance (LOA) was issued on 26th May 2016 and work order was issued on 27th July 2016, but work started at site on 27/12/2016. Later on Contract Agreement was signed between GoAJ&K and Frontier Works Organization (FWO) on 09/06/2017. Now the Work is continuing with progress at the site. However the completion period of the project as per approved PC-1 has been expired, and now as per work schedule by the Contractor FWO, we required the extension in time up-to 31 December 2019 as per work schedule for completion of said project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 | Bottlenecks / issues in implementation of project, if any: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Project Director Leswa & Karen By-passes

(Superintending Engineer)

PWD Highways Circle Mzd

GOVERNMENT OF PAKISTAN

Planning Commission

Ministry of Planning, Development & Reform

(Public Investment Authorization Section)

### *******

Extension in execution period of development projects from DDWP / CDWP / ECNEC

- Name of sponsoring Ministry / Agency:	Kashmir Affairs & Gilgit Baltistan Division

- Name of Executing Agency: 			Public Works Department Govt. of AJ&K

- Sector / sub sector: 				T&C

(Rs. in million)

| 1 | Name of the Project: |  |  |  |  | Improvement Metalling & Black Topping of Authmuqam-Karen By-pass Road length 40-Km, District Neelum (AJ&K.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Location : |  |  |  |  | District Neelum |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Date of Approval: |  |  |  |  | DDWP |  |  |  |  | CDWP |  |  |  |  |  | ECNEC |  |  |  |
| (a) | Original: |  |  |  |  |  |  |  |  |  | 26/12/2013 |  |  |  |  |  |  |  |  |  |
| (b) | Last revised, if any: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Approved cost : |  |  |  |  | Total |  |  |  |  | Local |  |  |  |  |  | FEC |  |  |  |
| (a) | Original: |  |  |  |  | 765.653 Million |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (b) | Last revised, if any: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Objectives (in bullet form) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Commencement date |  |  |  |  | As per original PC-I |  |  |  |  |  |  | Actual |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 25/06/2014 |  |  |  |  |  |  | 27/12/2016 |  |  |  |  |  |  |  |
| 7 | Completion Date |  |  |  |  | As per original / revised PC-I |  |  |  |  |  |  | Expected |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 30th June 2017 |  |  |  |  |  |  | 28th February 2020 |  |  |  |  |  |  |  |
| 8 | Year-wise financial phasing, releases and utilization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Fiscal Year |  | Phasing as per approved PC-I (latest) |  | PSDP allocation |  |  |  | Actual amount released |  |  |  |  |  |  | Actual utilization |  |  |  |  |
|  |  |  | Total | FEC | Total |  | FEC |  | Total |  |  | FEC |  |  | Total |  |  |  | FEC |  |
|  | 1 |  | 2 | 3 | 4 |  | 5 |  | 6 |  |  | 7 |  |  | 8 |  |  |  | 9 |  |
|  | 2014-15 |  | 279.439 | - | 100.000 |  | - |  | 100.000 |  |  | - |  |  | 1.000 |  |  |  | - |  |
|  | 2015-16 |  | 256.488 | - | 100.000 |  | - |  | 100.000 |  |  | - |  |  | - |  |  |  | - |  |
|  | 2016-17 |  | 229.726 | - | 80.000 |  | - |  | 80.000 |  |  | - |  |  | 80.000 |  |  |  | - |  |
|  | 2017-18 |  | - | - | 485.653 |  | - |  | 30.000 |  |  | - |  |  | 26.760 |  |  |  | - |  |
| 9 | Itemized cost as per approved PC-I and utilization (major items) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | S # | Major items |  |  |  |  |  | PC-I Provision |  |  |  |  |  | Cumulative utilization upto date |  |  |  | Balance |  |  |
|  |  |  |  |  |  |  |  | Quantity |  | Cost estimates |  |  |  |  |  |  |  | Work to be done (Qty) |  | Funds required |
|  | 1 | 2 |  |  |  |  |  | 3 |  | 4 |  |  |  | 5 |  |  |  | 6 |  | 7 |
|  | i | Earth Work i/c filling |  |  |  |  |  | 10196800 (Cft) |  | 63.624 |  |  |  | 23.216 |  |  |  | 4505431 (cft) |  |  |
|  | ii | Retaining Structure i/c all activities |  |  |  |  |  | 1551161 (Cft) |  | 126.475 |  |  |  | 5.893 |  |  |  | 1417835 (cft) |  |  |
|  | iii | Cross Drainage |  |  |  |  |  | 100 (No.) |  | 64.366 |  |  |  | 2.142 |  |  |  | 85 (Nos) |  |  |
|  | iv | Mett: & B Topping (Premix) |  |  |  |  |  | 40-Km |  | 416.536 |  |  |  | - |  |  |  | 40-Km |  |  |
|  | v | Parapets |  |  |  |  |  | 8500 (Nos) |  | 25.806 |  |  |  | - |  |  |  | 8500 (Nos) |  |  |
|  | vi | Escalation/Contingencies/slop Protection |  |  |  |  |  | - |  | 68.846 |  |  |  | - |  |  |  | - |  |  |
| 10. | - Physical progress ( % ): Earth Work 56% Sub base & base course 25% Asphalt 0% Cross Drainage 15% Retaining Structure 9% Parapets 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 | No. of previous extensions ( indicate approving authority and period with dates): Nil |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 | Extension required ( indicate period with dates): 28th February 2020 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13. | Main reasons / justification for extension: PC-1 of above mentioned project was approved CDWP through Ministry of Kashmir Affairs and Gilgit Biltistan on 26th December 2013 at cost of Rs. 765.653 Million and Admin approval was issued on 25th June 2014. The Federal Govt. approved the award of said project to FWO on single source basis vide No. PC/18/2013 dated 24th August 2015. FWO received the bidding documents on 22-09-2015. FWO submitted their rates on 03/12/2015 which were much higher than the approved PC-I rates. Series of meetings at different places and forums were held about the rationalization of rates for said project with FWO. FWO was submitted their rationalized rates on 25th May 2016 and then Letter of Acceptance (LOA) was issued on 26th May 2016 and work order was issued on 27th July 2016, but work started at site on 24/03/2017. Later on Contract Agreement was signed between GoAJ&K and Frontier Works Organization (FWO) on 09/06/2017. Work is continuing with progress at the site. However the completion period of the project as per approved PC-1 has been expired, and now as per work schedule by the Contractor FWO, we required the extension in time up-to 28th February 2020 as per work schedule for completion of said project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 | Bottlenecks / issues in implementation of project, if any: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Project Director Leswa & Karen By-passes

(Superintending Engineer)

PWD Highways Circle Mzd